## Simple Gantt Chart - EX
CAPSTONE PROJECT AND RESEARCH 2 GANTT CHART
CAPSTONE PROJECT TITLE | AI-Powered Predictive Analytics for an Academic Early Warning System
NAME OF STUDENTS | Kendrick O. Amparado, Christian Dave E. Pombo, Ian Carlo B. Quimbo, Kent Ian C. Seridon
NAME OF ADVISER | Czarissa Louise A. Navidad
SECTION CODE / SCHEDULE | T299 / TF 3:00PM-5:30PM
OVERALL ACCOMPLISHMENT | 79.03% | as of | 02/13/26, 4:16 PM
[8 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | % OF TASK |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE |  | M | T | W | T | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Auth & account
1 | Login page – frontend | Quimbo | 2026-01-19 | 2026-01-20 | 1 | 100% | 1 | bar: WEEK 1 M to WEEK 1 T; WEEK 2 W
2 | SignUp page – frontend | Quimbo | 2026-01-19 | 2026-01-20 | 1 | 100% | 1 | bar: WEEK 1 M to WEEK 1 T; WEEK 2 W
3 | Check email page – frontend | Quimbo | 2026-01-19 | 2026-01-20 | 1 | 100% | 1 | bar: WEEK 1 M to WEEK 1 T; WEEK 2 W
4 | Pending approval page – frontend | Quimbo | 2026-01-19 | 2026-01-20 | 1 | 100% | 1 | bar: WEEK 1 M to WEEK 1 T; WEEK 2 W
5 | Verify email page – frontend | Quimbo | 2026-01-19 | 2026-01-20 | 1 | 100% | 1 | bar: WEEK 1 M to WEEK 1 T; WEEK 2 W
6 | Forgot password page – frontend | Quimbo | 2026-01-19 | 2026-01-20 | 1 | 100% | 1 | bar: WEEK 1 M to WEEK 1 T; WEEK 2 W
7 | Reset password page – frontend | Quimbo | 2026-01-19 | 2026-01-20 | 1 | 100% | 1 | bar: WEEK 1 M to WEEK 1 T; WEEK 2 W
8 | Auth API: POST login – backend | Quimbo | 2026-01-19 | 2026-01-20 | 1 | 100% | 1 | bar: WEEK 1 M to WEEK 1 T; WEEK 2 W
9 | Auth API: POST signup – backend | Quimbo | 2026-01-19 | 2026-01-20 | 1 | 100% | 1 | bar: WEEK 1 M to WEEK 1 T; WEEK 2 W
10 | Auth API: GET verify-email – backend | Quimbo | 2026-01-19 | 2026-01-21 | 2 | 100% | 1 | bar: WEEK 1 M to WEEK 1 W; WEEK 2 W
11 | Auth API: POST forgot-password – backend | Quimbo | 2026-01-19 | 2026-01-21 | 2 | 100% | 1 | bar: WEEK 1 M to WEEK 1 W; WEEK 2 W
12 | Auth API: POST reset-password – backend | Quimbo | 2026-01-19 | 2026-01-21 | 2 | 100% | 1 | bar: WEEK 1 M to WEEK 1 W; WEEK 2 W
13 | Auth API: GET email-status, GET test-email – backend | Quimbo | 2026-01-19 | 2026-01-21 | 2 | 100% | 1 | bar: WEEK 1 M to WEEK 1 W; WEEK 2 W
14 | Auth context and protected routes – frontend | Quimbo | 2026-01-19 | 2026-01-21 | 2 | 100% | 1 | bar: WEEK 1 M to WEEK 1 W; WEEK 2 W
15 | Admin approval flow: instructor/amu-staff signup → pending; admin confirm/decline – backend | Quimbo | 2026-01-19 | 2026-01-21 | 2 | 100% | 1 | bar: WEEK 1 M to WEEK 1 W; WEEK 2 W
16 | Admin pending-accounts list API – backend | QUimbo | 2026-01-20 | 2026-01-21 | 1 | 100% | 1 | bar: WEEK 1 T to WEEK 1 W; WEEK 2 W
17 | Admin pending-accounts approve/decline API – backend | QUimbo | 2026-01-20 | 2026-01-21 | 1 | 100% | 1 | bar: WEEK 1 T to WEEK 1 W; WEEK 2 W
18 | Account decision emails (approved/declined) – backend | Quimbo | 2026-01-20 | 2026-01-21 | 1 | 100% | 1 | bar: WEEK 1 T to WEEK 1 W; WEEK 2 W
19 | Admin Pending accounts tab – frontend | Quimbo | 2026-01-20 | 2026-01-21 | 1 | 100% | 1 | bar: WEEK 1 T to WEEK 1 W; WEEK 2 W
Instructor
20 | Instructor dashboard page – frontend | Quimbo | 2026-01-20 | 2026-01-21 | 1 | 100% | 1 | bar: WEEK 1 T to WEEK 1 W; WEEK 2 W
21 | Instructor My Classes tab – frontend | Quimbo | 2026-01-20 | 2026-01-21 | 1 | 100% | 1 | bar: WEEK 1 T to WEEK 1 W; WEEK 2 W
22 | Instructor Risk Alerts tab – frontend | Quimbo | 2026-01-20 | 2026-01-21 | 1 | 100% | 1 | bar: WEEK 1 T to WEEK 1 W; WEEK 2 W
23 | Instructor Student List tab – frontend | Quimbo | 2026-01-20 | 2026-01-21 | 1 | 100% | 1 | bar: WEEK 1 T to WEEK 1 W; WEEK 2 W
24 | Instructor Interventions tab – frontend | Quimbo | 2026-01-20 | 2026-01-21 | 1 | 100% | 1 | bar: WEEK 1 T to WEEK 1 W; WEEK 2 W
25 | Class details page – frontend | Quimbo | 2026-01-20 | 2026-01-21 | 1 | 100% | 1 | bar: WEEK 1 T to WEEK 1 W; WEEK 2 W
26 | Add class modal – frontend | Quimbo | 2026-01-20 | 2026-01-21 | 1 | 100% | 1 | bar: WEEK 1 T to WEEK 1 W; WEEK 2 W
27 | Add student / batch add students – frontend | Quimbo | 2026-01-20 | 2026-01-21 | 1 | 100% | 1 | bar: WEEK 1 T to WEEK 1 W; WEEK 2 W
28 | Instructor intervention detail page – frontend | Quimbo | 2026-01-20 | 2026-01-21 | 1 | 100% | 1 | bar: WEEK 1 T to WEEK 1 W; WEEK 2 W
29 | Instructor student profile page – frontend | Quimbo | 2026-01-23 | 2026-01-24 | 1 | 100% | 1 | bar: WEEK 2 W
30 | Instructor settings page – frontend | Quimbo | 2026-01-23 | 2026-01-24 | 1 | 100% | 1 | bar: WEEK 1 F; WEEK 2 W
31 | Classes API: list, get, create – backend | Quimbo | 2026-01-23 | 2026-01-24 | 1 | 100% | 1 | bar: WEEK 1 F; WEEK 2 W
32 | Classes API: list students, risk-summary – backend | Quimbo | 2026-01-23 | 2026-01-24 | 1 | 100% | 1 | bar: WEEK 1 F; WEEK 2 W
33 | Classes API: add student, batch add – backend | Quimbo | 2026-01-23 | 2026-01-24 | 1 | 100% | 1 | bar: WEEK 1 F; WEEK 2 W
34 | Classes API: risk-alerts, instructor-students – backend | Quimbo | 2026-01-23 | 2026-01-24 | 1 | 100% | 1 | bar: WEEK 1 F; WEEK 2 W
35 | Interventions API: list, get – backend | Quimbo | 2026-01-23 | 2026-01-24 | 1 | 100% | 1 | bar: WEEK 1 F; WEEK 2 W
36 | Instructor first-login tutorial popup – frontend | Quimbo | 2026-01-23 | 2026-01-24 | 1 | 100% | 1 | bar: WEEK 1 F; WEEK 2 W
37 | Instructor settings tutorial section (play every login, play again) – frontend | Quimbo | 2026-01-23 | 2026-01-24 | 1 | 100% | 1 | bar: WEEK 1 F; WEEK 2 W
Admin
38 | Admin dashboard page – frontend | Quimbo | 2026-01-23 | 2026-01-24 | 1 | 100% | 1 | bar: WEEK 1 F; WEEK 2 W
39 | Admin System Overview tab – frontend | Quimbo | 2026-01-26 | 2026-01-27 | 1 | 100% | 1 | bar: WEEK 2 M to WEEK 2 W
40 | Admin department dropdown (instructor departments only) – frontend | Quimbo | 2026-01-26 | 2026-01-27 | 1 | 100% | 1 | bar: WEEK 2 M to WEEK 2 W
41 | Admin Students at Risk sub-tab – frontend | Quimbo | 2026-01-26 | 2026-01-27 | 1 | 100% | 1 | bar: WEEK 2 M to WEEK 2 W
42 | Admin Departments sub-tab – frontend | Quimbo | 2026-01-26 | 2026-01-27 | 1 | 100% | 1 | bar: WEEK 2 M to WEEK 2 W
43 | Admin Instructors sub-tab – frontend | Quimbo | 2026-01-26 | 2026-01-27 | 1 | 100% | 1 | bar: WEEK 2 M to WEEK 2 W
44 | Admin overview trends chart – frontend | Quimbo | 2026-01-26 | 2026-01-27 | 1 | 100% | 1 | bar: WEEK 2 M to WEEK 2 W
45 | Admin System Analytics tab – frontend | Quimbo | 2026-01-26 | 2026-01-28 | 2 | 100% | 1 | bar: WEEK 2 M to WEEK 2 W
46 | Admin Institution Reports tab – frontend | Quimbo | 2026-01-26 | 2026-01-28 | 2 | 100% | 1 | bar: WEEK 2 M to WEEK 2 W
47 | Admin User Accounts tab – frontend | Quimbo | 2026-01-26 | 2026-01-28 | 2 | 100% | 1 | bar: WEEK 2 M to WEEK 2 R
48 | Admin Interventions tab – frontend | Quimbo | 2026-01-26 | 2026-01-28 | 2 | 100% | 1 | bar: WEEK 2 M to WEEK 2 R
49 | Admin user detail page – frontend | Quimbo | 2026-01-26 | 2026-01-28 | 2 | 100% | 1 | bar: WEEK 2 M to WEEK 2 R
50 | Admin intervention detail page – frontend | Quimbo | 2026-01-26 | 2026-01-28 | 2 | 100% | 1 | bar: WEEK 2 M to WEEK 2 R
51 | Admin student detail page (by email) – frontend | Quimbo | 2026-01-28 | 2026-01-29 | 1 | 100% | 1 | bar: WEEK 2 W to WEEK 2 R
52 | Admin settings page – frontend | Quimbo | 2026-01-28 | 2026-01-29 | 1 | 100% | 1 | bar: WEEK 2 W to WEEK 2 R
53 | Admin API: departments (instructor only) – backend | Quimbo | 2026-01-28 | 2026-01-29 | 1 | 100% | 1 | bar: WEEK 2 W to WEEK 2 R
54 | Admin API: overview, students-at-risk, departments, instructors, trends – backend | Quimbo | 2026-01-28 | 2026-01-29 | 1 | 100% | 1 | bar: WEEK 2 W to WEEK 2 R
55 | Admin API: analytics department-chart, risk-distribution, accuracy – backend | Quimbo | 2026-01-28 | 2026-01-29 | 1 | 100% | 1 | bar: WEEK 2 W to WEEK 2 R
56 | Admin API: reports list, report download (CSV) – backend | Quimbo | 2026-01-28 | 2026-01-29 | 1 | 100% | 1 | bar: WEEK 2 W to WEEK 2 R
57 | Admin API: student by email (enrollments) – backend | Quimbo | 2026-01-28 | 2026-01-29 | 1 | 100% | 1 | bar: WEEK 2 W to WEEK 2 R
58 | Users API: list, get, create, update, delete – backend | Quimbo | 2026-01-28 | 2026-01-29 | 1 | 100% | 1 | bar: WEEK 2 W to WEEK 2 R
Amu Staff
59 | AMU Staff dashboard page – frontend | Quimbo | 2026-02-01 | 2026-02-03 | 2 | 100% | 1 | bar: WEEK 2 W; WEEK 3 M to WEEK 3 W
60 | AMU Staff Overview tab – frontend | Quimbo | 2026-02-01 | 2026-02-03 | 2 | 100% | 1 | bar: WEEK 2 W; WEEK 3 M to WEEK 3 W
61 | AMU Staff Referrals tab – frontend | Quimbo | 2026-02-01 | 2026-02-03 | 2 | 100% | 1 | bar: WEEK 2 W; WEEK 3 M to WEEK 3 W
62 | AMU Staff My Cases tab – frontend | Quimbo | 2026-02-01 | 2026-02-03 | 2 | 100% | 1 | bar: WEEK 2 W; WEEK 3 M to WEEK 3 W
63 | AMU Staff Reports tab – frontend | Quimbo | 2026-02-01 | 2026-02-03 | 2 | 100% | 1 | bar: WEEK 2 W; WEEK 3 M to WEEK 3 W
64 | AMU Staff student detail page – frontend | Quimbo | 2026-02-01 | 2026-02-03 | 2 | 100% | 1 | bar: WEEK 2 W; WEEK 3 M to WEEK 3 W
65 | AMU Staff case detail page – frontend | Quimbo | 2026-02-01 | 2026-02-03 | 2 | 100% | 1 | bar: WEEK 2 W; WEEK 3 M to WEEK 3 W
66 | AMU Staff settings page – frontend | Quimbo | 2026-02-01 | 2026-02-03 | 2 | 100% | 1 | bar: WEEK 2 W; WEEK 3 M to WEEK 3 W
67 | AMU Staff first-login tutorial popup – frontend | Quimbo | 2026-02-01 | 2026-02-03 | 2 | 100% | 1 | bar: WEEK 2 W; WEEK 3 M to WEEK 3 W
68 | AMU Staff settings tutorial section – frontend | Quimbo | 2026-02-01 | 2026-02-03 | 2 | 100% | 1 | bar: WEEK 2 W; WEEK 3 M to WEEK 3 W
Shared / Infrastructure
69 | Dashboard layout (header, nav, notifications, logout, help) – frontend | Quimbo | 2026-02-05 | 2026-02-06 | 1 | 100% | 1 | bar: WEEK 2 W; WEEK 3 R to WEEK 3 F
70 | Notifications popover – frontend | Quimbo | 2026-02-05 | 2026-02-06 | 1 | 100% | 1 | bar: WEEK 2 W; WEEK 3 R to WEEK 3 F
71 | Notifications API: list by role, create, mark read, mark all read – backend | Quimbo | 2026-02-05 | 2026-02-06 | 1 | 100% | 1 | bar: WEEK 2 W; WEEK 3 R to WEEK 3 F
72 | Help / FAQ page – frontend | Quimbo | 2026-02-05 | 2026-02-06 | 1 | 100% | 1 | bar: WEEK 2 W; WEEK 3 R to WEEK 3 F
73 | NotFound (404) page – frontend | Quimbo | 2026-02-05 | 2026-02-06 | 1 | 100% | 1 | bar: WEEK 2 W; WEEK 3 R to WEEK 3 F
74 | Error boundary – frontend | Quimbo | 2026-02-05 | 2026-02-06 | 1 | 100% | 1 | bar: WEEK 2 W; WEEK 3 R to WEEK 3 F
75 | Global background image and enlarged content – frontend | Quimbo | 2026-02-05 | 2026-02-06 | 1 | 100% | 1 | bar: WEEK 2 W; WEEK 3 R to WEEK 3 F
76 | FastAPI app, CORS, health endpoint – backend | Quimbo | 2026-02-06 | 2026-02-07 | 1 | 100% | 1 | bar: WEEK 2 W; WEEK 3 R to WEEK 3 F
77 | MongoDB connection and role collections – backend | Quimbo | 2026-02-06 | 2026-02-07 | 1 | 100% | 1 | bar: WEEK 2 W; WEEK 3 R to WEEK 3 F
78 | User schemas and role-based collections – backend | Quimbo | 2026-02-06 | 2026-02-07 | 1 | 100% | 1 | bar: WEEK 2 W; WEEK 3 R to WEEK 3 F
79 | Interventions API: create, update, delete – backend | Quimbo | 2026-02-06 | 2026-02-07 | 1 | 100% | 1 | bar: WEEK 2 W; WEEK 3 R to WEEK 3 F
80 | Students API: list, get, create, update, delete – backend | Quimbo | 2026-02-06 | 2026-02-07 | 1 | 100% | 1 | bar: WEEK 2 W; WEEK 3 R to WEEK 3 F
AI & Prediction
81 | AI prediction pipeline (model, training, scoring) – backend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
82 | Store risk predictions in DB and prediction history – backend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
83 | Accuracy / metrics API (precision, recall over time) – backend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
84 | Admin AI Model tab – frontend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
85 | Admin AI Performance tab – frontend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
86 | System Analytics accuracy chart with real data – frontend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
87 | Instructor AI Feedback with real insights – frontend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
88 | AI-suggested interventions creation – backend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
89 | Interventions list “AI-suggested” source and create-from-AI – frontend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
Interventions Lifecycle
90 | Create intervention form (instructor / admin) – frontend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
91 | Update intervention status and notes from detail page – frontend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
92 | Intervention success outcome (improved / no change / declined) – backend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
93 | Intervention Success KPI and reports – backend + frontend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
94 | Link intervention to student (e.g. student id) for “View student” – backend + frontend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
Admin & Operations
95 | Add user form and button in User Accounts – frontend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
96 | Edit user form on User Detail – frontend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
97 | Admin interventions filter by instructor – backend + frontend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
98 | Seed / demo data script – backend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
Amu Staff & Student Experience
99 | AMU Staff Cases, Referrals, Reports with real API data – backend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
100 | AMU Staff components wired to real APIs – frontend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
101 | Student-facing app (login, view own risk) – frontend + backend (if in scope) |  |  |  |  | 0% | 0 | bar: WEEK 2 W
102 | Instructor Student Profile fully from real enrollment/risk APIs – frontend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
Polish & Scale
103 | Pagination for users, interventions, students lists – backend + frontend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
104 | Role-based API guards and 403 for admin-only – backend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
105 | Unit / integration tests – backend + frontend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
106 | Historical trends (time-series) for overview chart – backend |  |  |  |  | 0% | 0 | bar: WEEK 2 W
Profile & Settings
107 | Profile page redesign (all roles) | Amparado |  |  |  | 100% | 1 | bar: WEEK 2 W
108 | Profile image upload & API | Amparado |  |  |  | 100% | 1 | bar: WEEK 2 W
Admin & Instructor Layout
109 | Admin Container Design | Pombo |  |  |  | 100% | 1 | bar: WEEK 2 W
110 | Instructor tab content containers | Pombo |  |  |  | 100% | 1 | bar: WEEK 2 W
111 | Instructor detail/settings containers | Seridon |  |  |  | 100% | 1 | bar: WEEK 2 W
112 | Admin detail/settings containers | Seridon |  |  |  | 100% | 1 | bar: WEEK 2 W
113 | Profile image upload & API | Seridon |  |  |  | 100% | 1 | bar: WEEK 2 W
Institution Reports
114 | Generalized institution report UI | Quimbo |  |  |  | 100% | 1 | bar: WEEK 2 W
115 | Combined report download (backend) | Quimbo |  |  |  | 100% | 1 | bar: WEEK 2 W
Tutorial
116 | Role-based tutorial content | Quimbo |  |  |  | 100% | 1 | bar: WEEK 2 W
117 | Tutorial on admin (dashboard + settings) | Quimbo |  |  |  | 100% | 1 | bar: WEEK 2 W
Security & Robustness - Backend
118 | Login redirect by server role | Quimbo |  |  |  | 100% | 1 | bar: WEEK 2 W
119 | Dashboard auth and role guards | Quimbo |  |  |  | 100% | 1 | bar: WEEK 2 W
120 | AMU Staff API protection | Quimbo |  |  |  | 100% | 1 | bar: WEEK 2 W
121 | CORS from environment | Quimbo |  |  |  | 100% | 1 | bar: WEEK 2 W
122 | AMU Open case navigation fix | Quimbo |  |  |  | 100% | 1 | bar: WEEK 2 W
Backend / API
123 | User API profile_image | Quimbo |  |  |  | 100% | 1 | bar: WEEK 2 W
124 | Report download auth comment | Quimbo |  |  |  | 100% | 1 | bar: WEEK 2 W
125 | Uploading of Class List Roster in excel file | Quimbo |  |  |  | 100% | 1 | bar: WEEK 2 W
| Ian Carlo B. Quimbo | Christian Dave E. Pombo |  |  | Czarissa Louise A. Navidad |  |  | WEEK 2 M: Dr. Sales G. Aribe Jr.
| Researcher | Researcher |  |  | Adviser |  |  | WEEK 2 M: Instructor
| Kendrick O. Amparado | Kent Ian C. Seridon
| Researcher | Researcher